## Sheet1
TripWeave — 优先产品待办列表
用户故事ID | 功能ID | 优先级（MoSCoW） | 功能 / 用户故事 | 重写后的用户故事 | 故事点 | 实现技术 | 删除或者合并 | UserStory和Userflow做出区别，可以在一个userflow上生成userstory
US-01 | F-01 | 必须 | 注册、登录并访问个人行程 | 作为一名旅行者，我希望能够安全地注册和登录，以便保存、管理并访问仅属于我自己的旅行计划。 | 5 | 移动端（Kotlin、Android）、Web端（React）、后端（Spring Boot、Spring Security、JWT）、MySQL/PostgreSQL
US-02 | F-02 | 必须 | 直接粘贴旅行攻略文本 | 作为一名旅行者，我希望提交一个文本，以便复用其中有价值的旅行内容，而不需要手动复制每个地点和活动。 | 8 | 移动端/Web端文本编辑器、Spring Boot REST API、Python文本处理服务 | 用ML提取地名 | 本地化模型提取文本内的地名，减少token消耗（非必要，因为太难）
US-03 | F-03 | 必须 | 提取目的地、日期、地点和活动 | 作为一名旅行者，我希望系统从导入内容中提取目的地、日期、景点、餐厅、酒店和活动，以便将攻略转换为结构化旅行信息。 | 13 | Agentic AI / LLM结构化输出、Python NLP流程、JSON Schema校验、Spring Boot集成
US-04 | F-04 | 必须 | 保存提取出的旅行信息 | 作为一名旅行者，我希望系统保存提取出的地点和活动及其来源信息，以便之后查看时无需再次处理攻略。 | 5 | Spring Boot、Spring Data JPA、MySQL/PostgreSQL、imported_source、extracted_place和extracted_activity实体
US-05 | F-05 | 必须 | 使用地图数据验证提取地点 | 作为一名旅行者，我希望系统验证提取出的地点名称、地址和坐标，以便在生成行程前识别歧义或错误地点。 | 8 | Google Places API或OpenStreetMap/Nominatim、Spring Boot地图服务适配器、地理编码缓存 | 原本博客缺少详细地址怎么办（模糊搜索？）
US-06 | F-06 | 必须 | 检查提取出的旅行信息 | 作为一名旅行者，我希望在生成行程前检查提取出的日期、地点和活动，以便我仍然能够控制导入的信息。 | 5 | 移动端（Kotlin RecyclerView/Compose）或Web端（React）、Spring Boot检查API
US-07 | F-07 | 必须 | 修改、添加或删除提取地点 | 作为一名旅行者，我希望编辑、添加或删除提取出的地点和活动，以便不准确或不需要的内容不会进入最终行程。 | 5 | 移动端/Web端可编辑表单、Spring Boot CRUD API、输入校验、数据库持久化
US-08 | F-08 | 必须 | 根据确认后的信息创建行程 | 作为一名旅行者，我希望根据确认后的提取信息创建新行程，以便将导入攻略转化为已保存的旅行计划。 | 5 | Spring Boot行程服务、事务管理、MySQL/PostgreSQL、移动端/Web端确认流程
US-09 | F-09 | 必须 | 生成结构化的每日行程 | 作为一名旅行者，我希望系统将已确认的地点和活动组织为按天划分的行程，以便获得实际可执行的旅行计划。 | 8 | Agentic AI编排、业务规则、Spring Boot行程服务、Python规划服务
US-10 | F-10 | 必须 | 按天查看行程 | 作为一名旅行者，我希望查看每一天按顺序排列的活动、时间和地点，以便清楚了解每日安排。 | 5 | 移动端行程页面、Web端React时间线、Spring Boot Trip API、关系型数据库 | F9和F10重复
US-11 | F-11 | 必须 | 编辑行程活动 | 作为一名旅行者，我希望添加、修改、重新排序和删除行程活动，以便根据个人偏好和限制调整计划。 | 8 | 移动端拖拽排序/Web端React DnD、Spring Boot CRUD及排序API、数据库顺序字段
US-12 | F-12 | 必须 | 保存并重新打开行程 | 作为一名旅行者，我希望保存并重新打开行程，以便之后继续规划并在旅行过程中使用。 | 5 | Spring Boot、Spring Data JPA、MySQL/PostgreSQL、移动端/Web端行程列表与详情页
US-13 | F-13 | 必须 | 在交互式地图上显示行程地点 | 作为一名旅行者，我希望在交互式地图上查看行程中的所有地点，以便理解它们之间的地理关系。 | 8 | Android Google Maps SDK或同类方案、Web端Maps JavaScript API、后端地点坐标数据
US-14 | F-14 | 必须 | 计算路线、距离和旅行时间 | 作为一名旅行者，我希望查看行程地点之间的路线、距离和预计旅行时间，以便判断每日计划是否现实可行。 | 13 | Google Routes API / Directions API或同类服务、Spring Boot路线适配器、route_segments表
US-15 | F-15 | 必须 | 打开外部导航 | 作为一名旅行者，我希望在查看路线的时候可以跳转到Google map进行路线导航 | 5 | Android Intent、google.navigation
US-16 | F-16 | 必须 | 部署集成式云端环境 | 作为一名开发人员，我希望将Web端、后端、Python服务和数据库部署在同一云端环境中，以便所有客户端使用一致的集成系统。 | 8 | Docker、AWS/Azure/GCP、托管数据库、HTTPS、对象存储、环境变量和Secrets管理
US-17 | F-17 | 必须 | 建立CI/CD与安全扫描 | 作为一名开发人员，我希望每个Pull Request都自动构建、运行测试并执行安全扫描，以便在集成前发现损坏或不安全的代码。 | 5 | GitHub Actions、单元测试、SAST、依赖扫描、Secret扫描、Docker构建与部署流水线
US-18 | F-18 | 必须 | 推荐附近或相似地点 | 作为一名旅行者，我希望获得附近或相似地点的推荐，以发现更多符合兴趣的目的地。 | 8 | Python机器学习、Content-based Recommendation、TF-IDF/余弦相似度、Places API、推荐API、CSV-Singapore TripAdvisor 100 Dataset form Kaggle
US-19 | F-19 | 必须 | 收集旅行者偏好 | 作为一名旅行者，我希望设置美食、文化、自然或购物等兴趣偏好，以便生成的行程和推荐更符合我的需要。 | 5 | 移动端/Web端偏好表单、Spring Boot用户资料API、user_preferences表 | location-based database还是User habits的database | 用ML去提取关键信息比如出行人数，家庭成员，根据这些信息去给出ai推荐
US-20 | F-20 | 应该 | 导入处理完成后通知用户 | 作为一名旅行者，我希望在攻略导入完成后收到应用内或邮件通知，以便无需一直停留在处理页面。 | 5 | Spring Boot通知服务、邮件服务商或Firebase Cloud Messaging、notification表
US-21 | F-21 | 应该 | 查看个人行程摘要仪表盘 | 作为一名旅行者，我希望查看行程摘要统计，以了解地点数量、活动类别、旅行距离和旅行时间。 | 5 | React/Android图表、Chart.js或同类方案、Spring Boot分析API、SQL聚合
US-22 | F-22 | 应该 | 监控攻略导入记录 | 作为一名管理员，我希望查看导入记录、处理时长和失败原因，以识别运营问题并改善提取质量。 | 5 | 管理员Web端（React）、Spring Boot Admin API、导入日志、结构化日志
US-23 | F-23 | 应该 | 管理用户和不当内容 | 作为一名管理员，我希望管理用户账户并删除不当导入内容，以保持平台安全可靠。 | 5 | React管理员后台、Spring Security角色权限控制、Spring Boot内容管理API、审计日志
US-24 | F-24 | 应该 | 查看平台分析数据 | 作为一名管理员，我希望查看活跃用户、热门目的地、行程创建趋势和导入成功率，以评估平台使用情况和服务质量。 | 8 | React仪表盘、Chart.js、Spring Boot分析API、SQL聚合、云端监控
US-25 | F-25 | 应该 | 提供健康检查和结构化日志 | 作为一名开发人员，我希望系统具备健康检查、关联ID和结构化日志，以便在诊断问题时追踪Web端、后端和Python服务中的完整请求链路。 | 3 | Spring Boot Actuator、JSON日志、Correlation ID、Python结构化日志、云日志服务
US-26 | F-26 | 可以 | 分享只读行程 | 作为一名旅行者，我希望通过只读链接分享行程，以便朋友能够查看但不能修改我的计划。 | 5 | Spring Boot分享令牌API、Web公开行程页、链接过期和权限校验
US-27 | F-27 | 可以 | 将行程导出为PDF | 作为一名旅行者，我希望将行程导出为PDF，以便打印或保存便携副本。 | 5 | 后端PDF生成、HTML转PDF模板、Web/移动端下载流程
US-28 | F-28 | 可以 | 显示旅行日期天气 | 作为一名旅行者，我希望查看目的地和旅行日期的天气预报，以便调整活动并做好准备。 | 5 | 公共天气API（data.gov.sg/data.gov.sg（NEA））、Spring Boot天气适配器、Web/移动端天气组件
US-29 | F-29 | 可以 | 记录推荐反馈 | 作为一名旅行者，我希望接受或忽略推荐地点，以便未来的推荐更加符合我的兴趣。 | 5 | 移动端/Web端反馈控件、Spring Boot交互API、user_interactions表、机器学习反馈特征 | 可以提升为should级别
US-30 | F-30 | 可以 | 上传旅行攻略截图并进行OCR | 作为一名旅行者，我希望上传旅行内容截图，以便在只有图片时提取其中的文字。 | 13 | 移动端/Web端文件上传、云对象存储、OCR服务、Python预处理、文件校验
US-31 | F-31 | 可以 | 合作共享编辑旅行计划 | 作为一名旅行者，我希望可以和我的伙伴一起编辑，以便完善我们的计划。 | 13 | 移动端/Web端文件上传、云对象存储、OCR服务、Python预处理、文件校验
US-32 | F-32 | 可以 | 优化行程地点顺序 | 作为一名旅行者，我希望系统建议更高效的游览顺序，以减少地点之间不必要的旅行时间。 | 8 | 路线优化算法、地图路线矩阵API、Python优化服务、Spring Boot编排
US-33 | F-33 | 可以 | 体现景点各个时期人流量 | 作为一名旅行者，我希望系统能够预测景点人流量情况，以考虑出行顺序。 | 8 | TourismReceiptsByMajorComponentsYearToDateQuarterly.csv

## Sheet2
TripWeave — Prioritized Product Backlog
User Story ID | Feature ID | Priority (MoSCoW) | Feature / User Story | Rewritten User Story | Story Points | Implementation Technology
US-01 | F-01 | Must | Register, log in, and access personal itineraries | As a traveler, I want to register and log in securely so that I can save, manage, and access travel plans that belong only to me. | 5 | Mobile (Kotlin, Android), Web (React), Backend (Spring Boot, Spring Security, JWT), MySQL/PostgreSQL
US-02 | F-02 | Must | Paste travel guide text directly | As a traveler, I want to submit a piece of text so that I can reuse valuable travel content from it without manually copying every location and activity. | 8 | Mobile/Web text editor, Spring Boot REST API, Python text processing service
US-03 | F-03 | Must | Extract destination, dates, places, and activities | As a traveler, I want the system to extract destinations, dates, attractions, restaurants, hotels, and activities from imported content so that the guide can be converted into structured travel information. | 13 | Agentic AI / LLM structured output, Python NLP pipeline, JSON Schema validation, Spring Boot integration
US-04 | F-04 | Must | Save extracted travel information | As a traveler, I want the system to save the extracted places and activities together with their source information so that I can view them later without processing the guide again. | 5 | Spring Boot, Spring Data JPA, MySQL/PostgreSQL, imported_source, extracted_place, and extracted_activity entities
US-05 | F-05 | Must | Validate extracted places using map data | As a traveler, I want the system to validate the names, addresses, and coordinates of extracted places so that ambiguous or incorrect locations can be identified before generating the itinerary. | 8 | Google Places API or OpenStreetMap/Nominatim, Spring Boot map service adapter, geocoding cache | 给一个默认地点
US-06 | F-06 | Must | Review extracted travel information | As a traveler, I want to review the extracted dates, places, and activities before generating the itinerary so that I still have control over the imported information. | 5 | Mobile (Kotlin RecyclerView/Compose) or Web (React), Spring Boot review API
US-07 | F-07 | Must | Modify, add, or delete extracted places | As a traveler, I want to edit, add, or delete extracted places and activities so that inaccurate or unnecessary content does not enter the final itinerary. | 5 | Mobile/Web editable forms, Spring Boot CRUD API, input validation, database persistence
US-08 | F-08 | Must | Create an itinerary from confirmed information | As a traveler, I want to create a new itinerary from the confirmed extracted information so that the imported guide can be converted into a saved travel plan. | 5 | Spring Boot itinerary service, transaction management, MySQL/PostgreSQL, Mobile/Web confirmation flow
US-09 | F-09 | Must | Generate a structured daily itinerary | As a traveler, I want the system to organize confirmed places and activities into a day-by-day itinerary so that I can obtain a practical and executable travel plan. | 8 | Agentic AI orchestration, business rules, Spring Boot itinerary service, Python planning service
US-10 | F-10 | Must | View the itinerary by day | As a traveler, I want to view each day’s activities, times, and locations in sequence so that I can clearly understand the daily schedule. | 5 | Mobile itinerary page, Web React timeline, Spring Boot Trip API, relational database
US-11 | F-11 | Must | Edit itinerary activities | As a traveler, I want to add, modify, reorder, and delete itinerary activities so that I can adjust the plan according to personal preferences and constraints. | 8 | Mobile drag-and-drop sorting/Web React DnD, Spring Boot CRUD and sorting API, database order field
US-12 | F-12 | Must | Save and reopen itineraries | As a traveler, I want to save and reopen an itinerary so that I can continue planning later and use it during the trip. | 5 | Spring Boot, Spring Data JPA, MySQL/PostgreSQL, Mobile/Web itinerary list and detail pages
US-13 | F-13 | Must | Display itinerary places on an interactive map | As a traveler, I want to view all places in the itinerary on an interactive map so that I can understand their geographical relationships. | 8 | Android Google Maps SDK or an equivalent solution, Web Maps JavaScript API, backend place coordinate data
US-14 | F-14 | Must | Calculate routes, distances, and travel time | As a traveler, I want to view routes, distances, and estimated travel times between itinerary places so that I can determine whether the daily plan is realistic and feasible. | 13 | Google Routes API / Directions API or an equivalent service, Spring Boot route adapter, route_segments table
US-15 | F-15 | Must | Open external navigation | As a traveler, I want to redirect to Google Maps for route navigation while viewing a route. | 5 | Android Intent, google.navigation
US-16 | F-16 | Must | Deploy an integrated cloud environment | As a developer, I want to deploy the Web frontend, backend, Python service, and database in the same cloud environment so that all clients use a consistent integrated system. | 8 | Docker, AWS/Azure/GCP, managed database, HTTPS, object storage, environment variables, and Secrets management
US-17 | F-17 | Must | Establish CI/CD and security scanning | As a developer, I want every Pull Request to be built automatically, run tests, and perform security scans so that broken or insecure code can be identified before integration. | 5 | GitHub Actions, unit testing, SAST, dependency scanning, Secret scanning, Docker build and deployment pipeline
US-18 | F-18 | Must | Recommend nearby or similar places | As a traveler, I want to receive recommendations for nearby or similar places so that I can discover more destinations that match my interests. | 8 | Python machine learning, Content-based Recommendation, TF-IDF/cosine similarity, Places API, recommendation API, CSV-Singapore TripAdvisor 100 Dataset from Kaggle
US-19 | F-19 | Must | Collect traveler preferences | As a traveler, I want to set preferences such as food, culture, nature, or shopping so that generated itineraries and recommendations better match my needs. | 5 | Mobile/Web preference form, Spring Boot user profile API, user_preferences table |  | location-based trip-based user-based
US-20 | F-20 | Should | Notify users after import processing is completed | As a traveler, I want to receive an in-app or email notification after the guide import is completed so that I do not have to remain on the processing page. | 5 | Spring Boot notification service, email service provider or Firebase Cloud Messaging, notification table
US-21 | F-21 | Should | View a personal itinerary summary dashboard | As a traveler, I want to view itinerary summary statistics so that I can understand the number of places, activity categories, travel distance, and travel time. | 5 | React/Android charts, Chart.js or an equivalent solution, Spring Boot analytics API, SQL aggregation
US-22 | F-22 | Should | Monitor guide import records | As an administrator, I want to view import records, processing duration, and failure reasons so that I can identify operational issues and improve extraction quality. | 5 | Administrator Web frontend (React), Spring Boot Admin API, import logs, structured logging
US-23 | F-23 | Should | Manage users and inappropriate content | As an administrator, I want to manage user accounts and remove inappropriate imported content so that the platform remains safe and reliable. | 5 | React administrator backend, Spring Security role-based access control, Spring Boot content management API, audit logs
US-24 | F-24 | Should | View platform analytics data | As an administrator, I want to view active users, popular destinations, itinerary creation trends, and import success rates so that I can evaluate platform usage and service quality. | 8 | React dashboard, Chart.js, Spring Boot analytics API, SQL aggregation, cloud monitoring
US-25 | F-25 | Should | Provide health checks and structured logging | As a developer, I want the system to provide health checks, correlation IDs, and structured logs so that the complete request chain across the Web frontend, backend, and Python service can be traced when diagnosing issues. | 3 | Spring Boot Actuator, JSON logs, Correlation ID, Python structured logging, cloud logging service
US-26 | F-26 | Could | Share a read-only itinerary | As a traveler, I want to share an itinerary through a read-only link so that friends can view but cannot modify my plan. | 5 | Spring Boot sharing token API, public Web itinerary page, link expiration and permission validation
US-27 | F-27 | Could | Export the itinerary as PDF | As a traveler, I want to export the itinerary as a PDF so that I can print it or save a portable copy. | 5 | Backend PDF generation, HTML-to-PDF template, Web/Mobile download flow
US-28 | F-28 | Could | Display weather for travel dates | As a traveler, I want to view the weather forecast for the destination and travel dates so that I can adjust activities and prepare accordingly. | 5 | Public weather API (data.gov.sg/data.gov.sg (NEA)), Spring Boot weather adapter, Web/Mobile weather component
US-29 | F-29 | Could | Record recommendation feedback | As a traveler, I want to accept or ignore recommended places so that future recommendations better match my interests. | 5 | Mobile/Web feedback controls, Spring Boot interaction API, user_interactions table, machine learning feedback features
US-30 | F-30 | Could | Upload travel guide screenshots and perform OCR | As a traveler, I want to upload screenshots of travel content so that text can be extracted when only images are available. | 13 | Mobile/Web file upload, cloud object storage, OCR service, Python preprocessing, file validation
US-31 | F-31 | Could | Collaboratively share and edit travel plans | As a traveler, I want to edit together with my companions so that we can improve our plan. | 13 | Mobile/Web file upload, cloud object storage, OCR service, Python preprocessing, file validation
US-32 | F-32 | Could | Optimize the order of itinerary places | As a traveler, I want the system to recommend a more efficient visiting order so that unnecessary travel time between places can be reduced. | 8 | Route optimization algorithm, map route matrix API, Python optimization service, Spring Boot orchestration
US-33 | F-33 | Could | Show crowd levels at attractions during different periods | As a traveler, I want the system to predict crowd levels at attractions so that I can take them into consideration when planning my itinerary. | 8 | TourismReceiptsByMajorComponentsYearToDateQuarterly.csv
每个sprint做什么/每人有活干

## Sprint1-en
F-01 | User account management: register, log in / log out, view and edit personal information, view trip plans created by the user | User
F-02 | Create and manage trip plans: create a Trip, edit and delete a Trip, upload text / images, set destination, set start and end dates, view trip plans | Trip
F-02-01 | Collaborative editing: generate share links, invite collaborators | TRIP_MEMBER
F-02-02 | Schedule management: organize the trip plan by day | TripDay
F-02-03 | Activity ordering: break each day's plan into activities for ordering | ITINERARY_ITEM
F-03 | Location information: including geographic position and preference categories | Location
F-04 | Itinerary location status: including weather conditions and crowd levels, for API fetching | LocationStatus
F-05 | Map and route display: show location markers on the map, connect locations in itinerary order, show distances between locations, support different transport modes, show estimated travel time | Route
F-07 | Personal reviews: store user reviews of attractions | PersonalComment
F-08 | View trending destinations among active users | LocationRank

## Sprint1
| Feature | 主要操作 | 对应entity
F-01 | 用户账户管理 | 注册账户，登录登出，查看和修改个人信息，查看自己创建的旅行计划 | User
F-02 | 创建和管理旅行计划 | 创建Trip，修改和删除Trip，上传文本/图像，设置目的地，设置开始和结束日期，查看旅行计划 | Trip
F-02-01 | 共享编辑 | 生成分享链接，邀请协作 | TRIP_MEMBER
F-02-02 | 日程管理 | 把旅行计划按日分类 | TripDay
F-02-03 | 活动排序 | 把日程计划按照活动分割以排序 | ITINERARY_ITEM
F-03 | 地点信息 | 包括地理位置和喜好分类 | Location
F-04 | 行程地点状态 | 包括天气情况、人流量，供API抓取 | LocationStatus
F-05 | 地图和路线展示 | 在地图上显示地点marker，按行程顺序连接地点，显示地点之间的距离，支持不同交通方式，显示预计交通时间 | Route
F-07 | 个人评价 | 存储用户对景点的评价 | PersonalConment
F-08 |  | 查看活跃用户热门目的地 | LocationRank