## Product Backlog
TripWeave — Prioritized Product Backlog
User Story ID | Feature ID | Priority (MoSCoW) | Feature / User Story | Rewritten User Story | Story Points | Implementation Technology
US-01 | F-01 | Must | Register, log in, and access personal itineraries | As a traveler, I want to register and log in securely so that I can save, manage, and access travel plans that belong only to me. | 5 | Mobile (Kotlin, Android), Web (React), Backend (Spring Boot, Spring Security, JWT), MySQL/PostgreSQL
US-02 | F-02 | Must* | Paste travel guide text directly | As a traveler, I want to submit a piece of text so that I can reuse valuable travel content from it without manually copying every location and activity. | 8 | Mobile/Web text editor, Spring Boot REST API, Python text processing service
US-03 | F-03 | Must | Extract destination, dates, places, and activities | As a traveler, I want the system to extract destinations, dates, attractions, restaurants, hotels, and activities from imported content so that the guide can be converted into structured travel information. | 13 | Agentic AI / LLM structured output, Python NLP pipeline, JSON Schema validation, Spring Boot integration
US-04 | F-04 | Must | Save extracted travel information | As a traveler, I want the system to save the extracted places and activities together with their source information so that I can view them later without processing the guide again. | 5 | Spring Boot, Spring Data JPA, MySQL/PostgreSQL, imported_source, extracted_place, and extracted_activity entities
US-05 | F-05 | Must* | Validate extracted places using map data | As a traveler, I want the system to validate the names, addresses, and coordinates of extracted places so that ambiguous or incorrect locations can be identified before generating the itinerary. | 8 | Google Places API or OpenStreetMap/Nominatim, Spring Boot map service adapter, geocoding cache
US-06 | F-06 | Must | Review extracted travel information | As a traveler, I want to review the extracted dates, places, and activities before generating the itinerary so that I still have control over the imported information. | 5 | Mobile (Kotlin RecyclerView/Compose) or Web (React), Spring Boot review API
US-07 | F-07 | Must | Modify, add, or delete extracted places | As a traveler, I want to edit, add, or delete extracted places and activities so that inaccurate or unnecessary content does not enter the final itinerary. | 5 | Mobile/Web editable forms, Spring Boot CRUD API, input validation, database persistence
US-08 | F-08 | Must | Create an itinerary from confirmed information | As a traveler, I want to create a new itinerary from the confirmed extracted information so that the imported guide can be converted into a saved travel plan. | 5 | Spring Boot itinerary service, transaction management, MySQL/PostgreSQL, Mobile/Web confirmation flow
US-09 | F-09 | Must | Generate a structured daily itinerary | As a traveler, I want the system to organize confirmed places and activities into a day-by-day itinerary so that I can obtain a practical and executable travel plan. | 8 | Agentic AI orchestration, business rules, Spring Boot itinerary service, Python planning service
US-10 | F-10 | Must | View the itinerary by day | As a traveler, I want to view each day’s activities, times, and locations in sequence so that I can clearly understand the daily schedule. | 5 | Mobile itinerary page, Web React timeline, Spring Boot Trip API, relational database
US-11 | F-11 | Must | Edit itinerary activities | As a traveler, I want to add, modify, reorder, and delete itinerary activities so that I can adjust the plan according to personal preferences and constraints. | 8 | Mobile drag-and-drop sorting/Web React DnD, Spring Boot CRUD and sorting API, database order field
US-12 | F-12 | Must | Save and reopen itineraries | As a traveler, I want to save and reopen an itinerary so that I can continue planning later and use it during the trip. | 5 | Spring Boot, Spring Data JPA, MySQL/PostgreSQL, Mobile/Web itinerary list and detail pages
US-13 | F-13 | Must | Display itinerary places on an interactive map | As a traveler, I want to view all places in the itinerary on an interactive map so that I can understand their geographical relationships. | 8 | Android Google Maps SDK or an equivalent solution, Web Maps JavaScript API, backend place coordinate data
US-14 | F-14 | Must | Calculate routes, distances, and travel time | As a traveler, I want to view routes, distances, and estimated travel times between itinerary places so that I can determine whether the daily plan is realistic and feasible. | 13 | Google Routes API / Directions API or an equivalent service, Spring Boot route adapter, route_segments table
US-15 | F-15 | Must | Open external navigation | As a traveler, I want to jump to Google Maps for route navigation while viewing a route. | 5 | Android Intent, google.navigation
US-16 | F-16 | Must | Deploy an integrated cloud environment | As a developer, I want to deploy the Web frontend, backend, Python service, and database in the same cloud environment so that all clients use a consistent integrated system. | 8 | Docker, AWS/Azure/GCP, managed database, HTTPS, object storage, environment variables, and Secrets management
US-17 | F-17 | Must | Establish CI/CD and security scanning | As a developer, I want every Pull Request to be built automatically, run tests, and perform security scans so that broken or insecure code can be identified before integration. | 5 | GitHub Actions, unit testing, SAST, dependency scanning, Secret scanning, Docker build and deployment pipeline
US-18 | F-18 | Must | Recommend nearby or similar places | As a traveler, I want to receive recommendations for nearby or similar places so that I can discover more destinations that match my interests. | 8 | Python machine learning, Content-based Recommendation, TF-IDF/cosine similarity, Places API, recommendation API, CSV-Singapore TripAdvisor 100 Dataset from Kaggle
US-19 | F-19 | Must | Collect traveler preferences | As a traveler, I want to set preferences such as food, culture, nature, or shopping so that generated itineraries and recommendations better match my needs. | 5 | Mobile/Web preference form, Spring Boot user profile API, user_preferences table
US-20 | F-20 | Should | Notify users after import processing is completed | As a traveler, I want to receive an in-app or email notification after the guide import is completed so that I do not have to remain on the processing page. | 5 | Spring Boot notification service, email service provider or Firebase Cloud Messaging, notification table
US-21 | F-21 | Should | View a personal itinerary summary dashboard | As a traveler, I want to view itinerary summary statistics so that I can understand the number of places, activity categories, travel distance, and travel time. | 5 | React/Android charts, Chart.js or an equivalent solution, Spring Boot analytics API, SQL aggregation
US-22 | F-22 | Should | Monitor guide import records | As an administrator, I want to view import records, processing duration, and failure reasons so that I can identify operational issues and improve extraction quality. | 5 | Administrator Web frontend (React), Spring Boot Admin API, import logs, structured logging
US-23 | F-23 | Should | Manage users and inappropriate content | As an administrator, I want to manage user accounts and remove inappropriate imported content so that the platform remains safe and reliable. | 5 | React administrator backend, Spring Security role-based access control, Spring Boot content management API, audit logs
US-24 | F-24 | Should | View platform analytics data | As an administrator, I want to view active users, popular destinations, itinerary creation trends, and import success rates so that I can evaluate platform usage and service quality. | 8 | React dashboard, Chart.js, Spring Boot analytics API, SQL aggregation, cloud monitoring
US-25 | F-25 | Should | Provide health checks and structured logging | As a developer, I want the system to provide health checks, correlation IDs, and structured logs so that the complete request chain across the Web frontend, backend, and Python service can be traced when diagnosing issues. | 3 | Spring Boot Actuator, JSON logs, Correlation ID, Python structured logging, cloud logging service
US-26 | F-26 | Could | Share a read-only itinerary | As a traveler, I want to share an itinerary through a read-only link so that friends can view but cannot modify my plan. | 5 | Spring Boot sharing token API, public Web itinerary page, link expiration and permission validation
US-27 | F-27 | Could | Export the itinerary as PDF | As a traveler, I want to export the itinerary as a PDF so that I can print it or save a portable copy. | 5 | Backend PDF generation, HTML-to-PDF template, Web/Mobile download flow
US-28 | F-28 | Could | Display weather for travel dates | As a traveler, I want to view the weather forecast for the destination and travel dates so that I can adjust activities and prepare accordingly. | 5 | Public weather API (data.gov.sg/data.gov.sg (NEA)), Spring Boot weather adapter, Web/Mobile weather component
US-29 | F-29 | Could | Record recommendation feedback | As a traveler, I want to accept or ignore recommended places so that future recommendations better match my interests. | 5 | Mobile/Web feedback controls, Spring Boot interaction API, user_interactions table, machine learning feedback features
US-30 | F-30 | Could | Upload travel guide screenshots and perform OCR | As a traveler, I want to upload screenshots of travel content so that text can be extracted when only images are available. | 13 | Mobile/Web file upload, cloud object storage, OCR service, Python preprocessing, file validation
US-31 | F-31 | Could | Collaboratively share and edit travel plans | As a traveler, I want to edit together with my companions so that we can improve our plan. | 13 | Mobile/Web file upload, cloud object storage, OCR service, Python preprocessing, file validation
US-32 | F-32 | Could | Optimize the order of itinerary places | As a traveler, I want the system to recommend a more efficient visiting order so that unnecessary travel time between places can be reduced. | 8 | Route optimization algorithm, map route matrix API, Python optimization service, Spring Boot orchestration
US-33 | F-33 | Could | Show crowd levels at attractions during different periods | As a traveler, I want the system to predict crowd levels at attractions so that I can take them into consideration when planning my itinerary. | 8 | TourismReceiptsByMajorComponentsYearToDateQuarterly.csv
US-34 | F-34 | Could | Change travel itinerary base on personal schedule